## Prop Mgmt
Prop Mgmt / Admin
CLOSED | PRIMARY ACTIVITY | Priority | Update | Est Comp Date | Committee Responsible | Desired Outcome | Status
| Prop Mgmt (Dustin) to educate the Board on the current website, (www.valencia2.org) Cost for current domain/host - Frontsteps to include line item and PTD, adminstration cost as per Prop Mgmt Contract, and Cost comparison to switch to Go Daddy WIX | 1 | 11/18/19 GM |  | Prop Mgmt (Dustin) | Board provided sufficent data and information to determine the appropriate direction and next steps associated with VAL II's Website plans. | 11/11/19 Dustin will present the site at theh 11/18/19 GM. The domain has been released from Frontsteps and can go live at any time. the site can be live anytime. Pending Board direction at the 11/18/19 GM.
2019-11-01 | Update Valencia II's current Web Site with accurate/up to date info | 1 | 11/18/19 GM | December GM | Prop Mgmt (Leslie) and Lisa | Update current domain www.ValenciaII.org with pertinent information.
| Snow Property to provide an updated Scope of Services to Board | 1 | 11/18/19 GM |  | Prop Mgmt (Dustin) | Snow Properties will provide VAL II's Board with future service options and associated pricing. The Board will have ample opportunity to pose and receive responses to all questions allowing the Board to determine next steps and direction with Snow Properties | *This is an executive session item. As per action at the October meeting. Contract approval will require 3 Bids
| Ensure landowner repair of the blockwall on Cloud due to improper backyard lighting support installation. | 1 | 11/18/19 GM |  | Prop Mgmt (Dustin) | Exterior wall facing Cloud completely repaired
| Signage in front yards must have Board approval. Obtain information from Dustin regarding signage regulations | 1 | 11/18/19 GM |  | Prop Mgmt (Dustin) | Board level set on regulations and ensure effective communications to property owners
| Contracts - Create a contract summary sheet | 1 | 11/18/19 GM |  | Prop Mgmt (Dustin) | Summary sheet to contain all key information (e.g., contract term, expiration date, current status, identification of Val II signature, etc.) | 10/24/19 Lisa forwarded the copy she created to Dustin for review and updates. (Several of the contract copies the Board rcvd are not dated) Missing Estrella and the Park Maint Ins. Dustin has requested from the vendors.
| Provde update regarding the Resolution from issues in SS Pond (water quality, odor, foam) during the month of August. *Address all pond issues. | 1 | 11/18/19 GM |  | Prop Mgmt (Dustin) & LC (Jeff and Kevin) | 1. Research why the Estrella water report from August indicated NO PROBLEMS in the SS Pond. 2. Identification of what actions Estrella Water took to correct the situation and prevent this from reoccurring. | 10/24/19 Pond is still foamy and there is an odor 10/1/19 Dustin advised this has been resolved. Estrella was using new chemical that caused the issue
| Backyard lighting policy. Architecture committee to Draft policy and align board members | 1 | 11/18/19 GM |  | Prop Mgm (Snow) & AC(Tim) | Identification of specific CC&R's which apply as well as any additional steps or actions the Board should take to effectively manage this item. | 10/30/19 Pending Website, Quarterly Newsletter. Still needs communicated to the members. CCRs listed in the September minutes. Still needs to be added to the website and commnunicated to the HO.
| Identify specific actions and associated time frame to resolve the lien issue which originated with TW Lewis. | 1 | 12/9/19 GM |  | Prop Mgmt (Dustin) | Identify actions and time frame to Valencia Board. This should include (but not be limited to) a presentation from our lawyer to the Board. | 10/30/19 The Board requests a legal opinion/upate (written or present at the meeting)
| Make preparations for next Prom or Home Coming event. | 1 | By March 2020 GM |  | Prop Mgmt (Dustin) and Board Members(David and Lisa) | Establish communications with appropriate local high schools and determine the potential for onsite support (e.g., The Boy Scouts, etc.)
| Prop Mgmt (Dustin) to provide invoices and PTD for over budget line items, identified in the Treasurer's email dated 10/14/19 and at the 10/14/19 GM | 1 | By the 11/18/19 GM |  | Prop Mgmt (Dustin) | Review of invoice and PTD necessary for the CC to address the following item. *CC and Prop Mgmt to provide explanation on the overbudgeted line items and identify efficiencies to hold the budget flat. | *10/23/19 Dustin advised Jeff and Lisa that he would provide invoices/expenditures and explanation for all line items in question.
| CC and Prop Mgmt to provide explanation on the overbudgeted line items and identify efficiencies to hold the budget flat. | 1 | By the 11/18/19 GM |  | Prop Mgmt (Dustin) & Respective Comm |  | See FC David's email dated 10/14/19 and request during the GM on 10/14/19.
| Contracts - Analysis of all Contracts (terms and performances) and go out for bid for all contracts over $5K | 1 |  |  | Respective Comm and Prop Mgmt | Ensure current contract terms, scope of work, reporting structure and invoice approval.
| Confirm Valencia II as a non-profit | 1 |  | 11/18/19 GM |  |  | 11/11/19 Dustin confirmed Valencia II as a non-profit. The HOA has been paying non-resident and business rates for the meeting room. Dustin suggested we change the name /billing information from Snow to Valencia II as a non profit. (Dustin said he would speak to Daniella/EEC prior to the Board meeting on 11/19/19.
| Set up EEC meeting room as non-profit. | 1 | November 18, 2019 |  |  | Ensure Val II is charged appropriate rate of $20/hr versus the $80/hr charged historically
| Address issue of number of trees in front yards per Valencia II Landscape Guidelines | 2 | January 2020 timeframe - after progress underway with wall/fence repair project |  | Prop Mgmt (Dustin) | Rank list of Contractors and potential list of clarifying questions | Contractor Rank List and potentially documented list of clarifying questions
| Establish 2020 Board Meeting Calendar | 2 | Present at January 2020 Board Meeting |  | Board | Ensure cont. strategic planning, room reservations and member notification
| Adopt reasonalbe rules regarding Golf Carts, mini and pocket bikes | 3 | Proposal for February 2020 Board Meeting | March 2020 GM | Prop Mgmt (Dustin)
| Conduct Basic HOA (Open Meetings/Records Training) | 3 |  | March 2020 GM | Prop Mgmt (Dustin) | Ensure fundamental and OMA requirements are being met

## Landscape
Landscape
CLOSED | PRIMARY ACTIVITY | Priority | Update | Est Comp Date | Committee Responsible | Desired Outcome | Status
| Boundary Walls Project | 1 | 11/18/19 GM |  | LC (Jeff and Kevin) | A plan which identifies the scope, problem statement, and the high level actions, sequence (including sequence options: example, paint versus repair), and associated time frames and the individuals involved to effect repairs and maintenance of Valencia II's block walls. and iron fences. Receive Board feedback and ultimately approval to proceed. | 10/14/19 GM, HC Presented a plan to address repair and maintenance for Valencia II's block walls and iron fences. MOTION to approve Proposed Next Steps as outlined in presentation and included in the Minutes. 10/31/19: BPC currently providing an estimate to identify actions and associated cost estimates for a 5 year period.
| Inspect all light poles (as we have determined any light poles situated in a watering area, like grass) are suspect for corrosion (correct irrigation issues which continue to result in water on the surface of the Sport Courts in various communities) | 1 | 11/18/19 GM |  | LC (Jeff and Kevin) | A formal document to share with the Board and Snow Property Management indicating all specific structures/issues requiring immediate attention and indicating the specific action required. | Sept GM theBoard directed Dustin at the September meeting to have DECA inpect. 10/31/19: BPC is preparing an estimate to inspect the fixtures and assess actions per engineering standards.
| Implement modifications (primarily landscape) modifications to San Sebastian drain area: north side of the common area near the entrance | 1 | 11/18/19 GM |  | LC (Jeff and Kevin) | Desert scape a minimal area where turf growth is impossible | Kevin and Jeff met with Peak (Jordan) and have downsized the scope of work - awaiting Peak estimate
| Work with Kevin (the gate supplier) to determine how best to ensure closure of all pedestrian gates and look at keypad alternatives. | 2 | 12/9/19 GM |  | LC (Jeff and Kevin) | Ensure the operational integrity of the keypads (handles) as well as gate closure. | At 11/18 meeting recommending a trial of a limited number of Kant Slam units.
| Cloud and Lindsay corner - fix wall and build trench so lawnmowers don’t cut into wall. Also repair the wall including exposed rebar. | 2 | 11/18/19 GM |  | LC (Jeff and Kevin) | Ensure this work will be completed at Peak's expense and determine next steps and associated timing. | Ocotber GM, Bill advised that Peak will provide bids in Nov.
| Adopt reasonable rules regarding Golf Carts and mini and pocket bikes | 2 | Q1 2020 |  |  | Rules and regulations which consider liability, safety, and community concerns.

## Finance
Finance
CLOSED | PRIMARY ACTIVITY | Priority | Update | Est Comp Date | Committee Responsible | Desired Outcome | Status
| *Presentation – main focus on the 5-year and 30-year outlook and how it relates to 2020 Budget *Align on plan and targets by year to build Reserve for long term major funding needs while maintaining current assets | 1 | 11/18/19 GM | January 2020 GM | FC (David) | Board approval of 2020 budget. The final objective is a 5 year plan. First step is to determine (from David) what is necessary to complete the 5 Year Plan and a timeframe for completion. | October GM, David added a 20-30 minutes presentation to the 11/18/19 GM to review budget and HOA Fee increase. Snow Properties to ensure the members get notification of this presentation.
| Presentation and Action regarding the 2020 Budget. | 1 | 12/9/19 GM |  | FC (David) | Approve the 2020
| Implement controls/process for invoice approval. Create and implement approval process on all invoices that are overbudgeted. | 2 | 12/9/19 GM |  | FC (David) | Ensure budget and line item compliance.

## Communication
Communication
CLOSED | PRIMARY ACTIVITY | Priority | Update | Est Comp Date | Committee Responsible | Desired Outcome | Status
| Communicate Survey Results and Indicate Associated Resulting Board Actions | 1 | 12/19/19 GM |  | CC (Brian) | Summarize the input received and indicate priority items/points/issues and indicate associated Board actions | Direction pending the 11/18/19 website presentation and live release date of the updates made to the current domain (ValenciaII.org) by Snow Prop. *Preliminary communicaton was released to residents in August 2019.

## Closed
Closed
PRIMARY ACTIVITY | Priority | COMPLETED DATE | Committee Responsible | Status
Repair cracked sidewalk (3 sections) in San Sebastian caused by vendor work installing surface drains | 1 | 2019-11-06 | Prop Mgmt (Dustin) | All 3 sections completely repaired
Legal opinion on what constitutes a quorum of the Board as it relates to Committee meetings. | 1 | 2019-10-31 | Prop Mgmt (Dustin) | 10/31/19 Dustin advised 4 or more members = a quorem.
Reestablish Committee Chairs and members | 1 | 10/29/2019 SS | Board | 10/29/19 SS, Chairspersons confirmed, Committee members pending legal opinion defining a quorem.
Install the Maximum Occupancy signs on the bridge located adjacent to Andorra | 1 | 2019-11-13 | Prop Mgmt (Dustin) & LC (Jeff and Kevin) | Signs on both sides of the bridge installed.